## Instructions
The Best Practice Checklist
The Best Practice Checklist is designed to guide and provide high level monitoring for AEM implementations. Based on personas, each role has a tailored set of required documents and deliverables (or inputs into deliverables) for each phase and milestone of a project. The goal of the Best Practice Checklist is to ensure alignment with customer goals across all roles. It ensures accountability and transparency throughout the project with all major stakeholders.
Goals of the Best Practice Checklist
Alignment with customer success definitions and goals
Transparency into the project via input from all roles across all phases
Guide the customer and project team to successful implementations
How to use the Best Practice Checklist
Each role is responsible for maintaining the documents and deliverables for each phase. This is used to roll up into the Project Heartbeat that delivers a highlevel gauge of the project health, progress, and quality.
Definition of Columns
Phase
Sections of the project plan that contain set milestones.
Milestone
Defined points within phases of the project with defined delierables and outcomes expected at each.
Required Documents
Documents that are required by that role in order to produce the deliverables.
Y/N
Y for yes the document was recieved. N for no the document was not recieved. Only Y, N or empty are recognized values. All other values will not factor into the calculation.
Quality 1-3
A 1 to 3 scale to rank the quality of the recieved docuents with 1 being poor and 3 being excellent. Only numerical values are recognized. All other values will not be factored into the calculation.
Deliverables
Documents, outputs or contributions to documents that are defined at each milestone.
Definitions of Calculations
Completeness
Percentage of the items filled in Y or N for the project against those that have been left empty.
Phase Health
A wieghed percentage of the items marked as Y or N based on the over importance to AEM projects in general that indicates the over health of a project.
Quality
An average of the quality grade (scale of 1-3) given to the item by the role utilizing it in the project.

## Project Heartbeat
AEM Project Heartbeat
|  | Preparation | Planning | Development Planning | Operations & Operations Planning | Development | Performance & Testing | Rollout | Go Live
Phase Quality |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Preparation | Planning | Development Planning | Operations & Operations Planning | Development | Performance & Testing | Rollout | Go Live
Phase Health |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | Preparation | Planning | Development Planning | Operations & Operations Planning | Development | Performance & Testing | Rollout | Go Live
Phase Completeness |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Milestones (Dates)

## Status by Role
AEM Status by Role
| Project Sponsor |  |  | Project Manager |  |  | Solution Architect |  |  | Business Analyst |  |  | Development Lead |  |  | Quality Lead |  |  | System Engineer |  |  | Security Lead |  |  | Averages
| Phase Health | Quality Level | Completeness | Phase Health | Quality Level | Completeness | Phase Health | Quality Level | Completeness | Phase Health | Quality Level | Completeness | Phase Health | Quality Level | Completeness | Phase Health | Quality Level | Completeness | Phase Health | Quality Level | Completeness | Phase Health | Quality Level | Completeness | Heartbeat | Quality | Completeness
Phase - Preparation
Sucess Indication | 0% |  | 0% | 0% |  | 0% | 0% |  | 0% | 0% |  | 0% | 0% |  | 0% | 0% |  | 0% | 0% |  | 0% | NA | NA | NA | 0% | 0 | 0%
Phase - Planning
Sucess Indication | 0% |  | 0% | 0% |  | 0% | 0% |  | 0% | 0% |  | 0% | 0% |  | 0% | 0% |  | 0% | 0% |  | 0% | 0% |  | 0% | 0% | 0 | 0%
Phase - Operations
Sucess Indication | 0% |  | 0% | 0% |  | 0% | 0% |  | 0% | NA | NA | NA | 0% |  | 0% | NA | NA | NA | 0% |  | 0% | 0% |  | 0% | 0% | 0 | 0%
Phase - Development Planning
Sucess Indication | 0% |  | 0% | 0% |  | 0% | 0% |  | 0% | 0% |  | 0% | 0% |  | 0% | 0% |  | 0% | 0% |  | 0% | 0% |  | 0% | 0% | 0 | 0%
Phase - Development
Sucess Indication | NA | NA | NA | 0% |  | 0% | 0% |  | 0% | 0% |  | 0% | 0% |  | 0% | 0% |  | 0% | 0% |  | 0% | NA | NA | NA | 0% | 0 | 0%
Phase - Performance & Testing
Sucess Indication | 0% |  | 0% | 0% |  | 0% | 0% |  | 0% | NA | NA | NA | 0% |  | 0% | 0% |  | 0% | 0% |  | 0% | NA | NA | NA | 0% | 0 | 0%
Phase - Rollout
Sucess Indication | 0% |  | 0% | 0% |  | 0% | 0% |  | 0% | NA | NA | NA | 0% |  | 0% | NA | NA | NA | 0% |  | 0% | 0% |  | 0% | 0% | 0 | 0%
Phase - Go Live
Sucess Indication | 0% |  | 0% | 0% |  | 0% | 0% |  | 0% | NA | NA | NA | 0% |  | 0% | 0% |  | 0% | 0% |  | 0% | 0% |  | 0% | 0% | 0 | 0%

## Project Sponsor
Phase | Milestone | Required Documents | Y/N | max | current | IWeight | Quality 1-3 | Deliverables | Y/N |  |  | DWeight
Preparation | Validation | Business Case(s) |  | FALSE |  | 50 |  | Customer Roadmap |  | FALSE |  | 20
|  | High Level Requirements |  | FALSE |  | 40 |  | Project Scope Document |  | FALSE |  | 40
|  | Stakeholders |  | FALSE |  | 20 |  | ROI expectations |  | FALSE |  | 30
|  | Success criteria and definition |  | FALSE |  | 30 |  | Initial Experience Designs |  | FALSE |  | 20
[8 empty] | Business Requirements Documentation |  | FALSE |  | 25
[8 empty] | Business KPIs |  | FALSE |  | 25
[8 empty] | Historical performance and historical performance KPIs |  | FALSE |  | 25
[8 empty] | Customer Security Policies |  | FALSE |  | 40
[8 empty] | Success criteria and definition |  | FALSE |  | 30
[8 empty] | Timeline and Milestones |  | FALSE |  | 25
| Budget | Project efforts final estimates |  | FALSE |  | 40 |  | Validated budget plan |  | FALSE |  | 40
|  | Contract Draft |  | FALSE |  | 40 |  | Finalized Contract |  | FALSE |  | 50
|  | Hardware Estimates |  | FALSE |  | 25
|  |  | 0% | 0 | 0 |  |  |  |  | 0 | 0
Planning | Handover | ROI expectations |  | FALSE |  | 30 |  | Performance KPIs |  | FALSE |  | 40
|  | Initial Experience Designs |  | FALSE |  | 20 |  | Project Scope Document |  | FALSE |  | 50
|  | Business Requirements Documentation |  | FALSE |  | 30 |  | Relevant contract terms |  | FALSE |  | 30
|  | High Level Requirements |  | FALSE |  | 35
|  | Architecture Draft |  | FALSE |  | 20
|  | Historical performance and historical performance KPIs |  | FALSE |  | 25
| Risk Assessment | Risk Assessment |  | FALSE |  | 50 |  | Identify critical key solutions/functionalities |  | FALSE |  | 40
|  | Proof of Concept (POC) |  | FALSE |  | 40 |  | Agreement on KPI's, defined as goals for the project |  | FALSE |  | 30
[8 empty] | Business sign off on any required adjustments to the solution or architecture identified and aligned against ROI and KPI expectations |  | FALSE |  | 50
[8 empty] | Technical risk factors verified |  | FALSE |  | 30
[8 empty] | Risk Mitigation Plan |  | FALSE |  | 45
| Communication | Customer Reporting Policies or Requirements |  | FALSE |  | 25 |  | Stakeholders |  | FALSE |  | 25
[8 empty] | Project status reports within a defined cadence |  | FALSE |  | 30
[8 empty] | Status Report format definition |  | FALSE |  | 25
[8 empty] | Reporting Cadence |  | FALSE |  | 20
[8 empty] | Customer Specification Guidelines |  | FALSE |  | 30
| Kick Off | Customer Roadmap |  | FALSE |  | 20 |  | Stakeholders understand project and expectations |  | FALSE |  | 30
|  | Project Scope Document |  | FALSE |  | 40 |  | Architecture Draft |  | FALSE |  | 50
|  | ROI expectations |  | FALSE |  | 25 |  | Stakeholders are aware of succes definitions and criteria |  | FALSE |  | 30
|  | Initial Experience Designs |  | FALSE |  | 20
|  | Requirements Documentation |  | FALSE |  | 40
|  | High Level Solution Design |  | FALSE |  | 30
|  | Architecture Draft |  | FALSE |  | 20
|  | Hardware Estimates |  | FALSE |  | 20
|  | Performance KPIs |  | FALSE |  | 40
|  | Timeline and Milestones |  | FALSE |  | 25
|  | Proof of Concept (POC) |  | FALSE |  | 20
|  | Success criteria and definition |  | FALSE |  | 35
|  |  | 0% | 0 | 0 |  |  |  |  | 0 | 0
Operations & Operations Planning | Permissions | Exisitng Permissions structure |  | FALSE |  | 40 |  | Roles and Rights Concept |  | FALSE |  | 35
| Monitoring & Maintenance | Customer Monitoring Policies or Requirements |  | FALSE |  | 40 |  | Monitoring Concept |  | FALSE |  | 30
| Migration | Legacy System |  | FALSE |  | 50 |  | Content validated for migration |  | FALSE |  | 40
| Recovery Plan | Operations Manual |  | FALSE |  | 50 |  | Customer Backup and restore policy |  | FALSE |  | 30
|  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0
Development Preparation | Support Setup | Setup Support processes |  | FALSE |  | 50 |  | List of users that require access to Adobe Support Portal |  | FALSE |  | 30
[8 empty] | Escalation Processes |  | FALSE |  | 30
|  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 60
Performance & Testing | (End-) user Acceptance Test | Release running on production environment |  | FALSE |  | 50 |  | Functionality of the solution are accepted by stakeholders |  | FALSE |  | 50
|  | Acceptance test |  | FALSE |  | 40
|  | Success criteria and definition |  | FALSE |  | 30
| Performance and Load-Test | Performance KPIs |  | FALSE |  | 40 |  | Acceptance from Business Stakeholders |  | FALSE |  | 50
|  | Use cases |  | FALSE |  | 25
|  | Testing Concept |  | FALSE |  | 40
|  | Performance Benchmark |  | FALSE |  | 30
|  | Performance Test Report |  | FALSE |  | 30
|  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0
Rollout | Admins trained | AEM Admin trainings |  | FALSE |  | 40 |  | Appropriately trained staff |  | FALSE |  | 40
|  | Training Materials |  | FALSE |  | 20
|  | User Guides |  | FALSE |  | 20
| Users trained | AEM Author trainings |  | FALSE |  | 30 |  | Appropriately trained staff |  | FALSE |  | 30
|  | Training Materials |  | FALSE |  | 20
|  | User Guides |  | FALSE |  | 20
| Pen Test | System Architecture Documentation |  | FALSE |  | 50
|  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0
Go-Live | Security | Security Checklist |  | FALSE |  | 40 |  | Customer Security Policies |  | FALSE |  | 40
|  | Penetration Test Results |  | FALSE |  | 40 |  | Security sign off from business stakeholders |  | FALSE |  | 50
| Fallback | Fallback system and procedure |  | FALSE |  | 40 |  | Fallback system sign off from business stakeholders |  | FALSE |  | 50
|  | Fallback system and procedure tested |  | FALSE |  | 30
| Support | Go live Schedule |  | FALSE |  | 50 |  | Resources available to support go live |  | FALSE |  | 45
| Transition | [6 empty] | Deployment / Release Policies and Processes |  | FALSE |  | 30
[8 empty] | Production Sign off Process and Policy |  | FALSE |  | 45
[8 empty] | Production Sign off from business stakeholders |  | FALSE |  | 50
|  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0

## Project Manager
Phase | Milestone | Required Documents | Y/N |  |  | W | Quality 1-3 | Deliverables | Y/N |  |  | W
Preparation | Validation | Customer Roadmap |  | FALSE |  | 5 |  | Project efforts initial estimates |  | FALSE |  | 25
|  | Project Scope Document |  | FALSE |  | 15 |  | Contract Draft |  | FALSE |  | 20
|  | ROI expectations |  | FALSE |  | 10 |  | Business KPIs |  | FALSE |  | 15
|  | Experience Designs Requirements |  | FALSE |  | 5 |  | Performance KPIs |  | FALSE |  | 25
|  | Business Requirements Documentation |  | FALSE |  | 20 |  | ROI expectations |  | FALSE |  | 15
|  | Technical Requirements |  | FALSE |  | 20 |  | Success criteria and definition |  | FALSE |  | 15
|  | Historical performance and historical performance KPIs |  | FALSE |  | 10
|  | Customer Security Policies |  | FALSE |  | 15
| Budget | Project Scope Document |  | FALSE |  | 20 |  | Validated budget plan |  | FALSE |  | 20
|  | High Level Solution Design |  | FALSE |  | 25 |  | Finalized Contract |  | FALSE |  | 45
|  | Hardware Estimates |  | FALSE |  | 25
|  | Requirements Documentation |  | FALSE |  | 30
|  | Project efforts final estimates |  | FALSE |  | 20
|  |  | 0% | 0 | 0 |  |  |  |  | 0 | 0
Planning | Handover | Customer Roadmap |  | FALSE |  | 15 |  | Performance KPIs |  | FALSE |  | 50
|  | Project Scope Document |  | FALSE |  | 30 |  | Understands scope of project and expectations |  | FALSE |  | 25
|  | ROI expectations |  | FALSE |  | 15 |  | Communicate scope and expectations to team |  | FALSE |  | 25
|  | Relevant contract terms |  | FALSE |  | 20 |  | Project Scope Document |  | FALSE |  | 20
|  | Business Requirements Documentation |  | FALSE |  | 20 |  | Project Ogranization |  | FALSE |  | 10
|  | Technical Requirements |  | FALSE |  | 20
| Risk Assessment | Identify critical key solutions/functionalities |  | FALSE |  | 20 |  | Technical risk factors verified |  | FALSE |  | 20
|  | Alignment of the customer roadmap with project timeline |  | FALSE |  | 15 |  | Business sign off on any required adjustments to the solution or architecture identified and aligned against ROI and KPI expectations |  | FALSE |  | 25
|  | Risk Assessment |  | FALSE |  | 45 |  | Risk Mitigation Plan |  | FALSE |  | 30
|  | Proof of Concept (POC) |  | FALSE |  | 20
| Communication | Stakeholders |  | FALSE |  | 20 |  | Issue tracking system process is set up and integrated |  | FALSE |  | 50
|  | Issue tracking system and processes |  | FALSE |  | 35 |  | Project communication plan |  | FALSE |  | 45
|  | Status Report format definition |  | FALSE |  | 25
|  | Reporting Cadence |  | FALSE |  | 20
| Kick Off | Customer Roadmap |  | FALSE |  | 5 |  | Team understands project and expectations |  | FALSE |  | 30
|  | Project Scope Document |  | FALSE |  | 10 |  | Alignment of the customer roadmap with project timeline |  | FALSE |  | 45
|  | ROI expectations |  | FALSE |  | 5 |  | Team is aware of the commmunication plan |  | FALSE |  | 25
|  | Initial Experience Designs |  | FALSE |  | 5 |  | Team is aware of succes definitions and criteria |  | FALSE |  | 15
|  | Requirements Documentation |  | FALSE |  | 15
|  | High Level Solution Design |  | FALSE |  | 10
|  | Architecture Draft |  | FALSE |  | 10
|  | Hardware Estimates |  | FALSE |  | 10
|  | Performance KPIs |  | FALSE |  | 5
|  | Timeline and Milestones |  | FALSE |  | 15
|  | Project Ogranization |  | FALSE |  | 10
|  | Success criteria and definition |  | FALSE |  | 15
|  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0
Development Preparation | Development Team trained / Staffing | AEM technical trainings |  | FALSE |  | 100 |  | Appropriately trained staff |  | FALSE |  | 50
| Content Architecture | Business KPIs |  | FALSE |  | 20 |  | Alignment on Content Architecture with KPIs |  | FALSE |  | 25
|  | Content Architecture Document |  | FALSE |  | 50
| System Architecture | Requirements Documentation |  | FALSE |  | 10 |  | Deployment / Release Policies and Processes |  | FALSE |  | 30
|  | High Level Solution Design |  | FALSE |  | 10 |  | Align Business and Performance KPIs |  | FALSE |  | 20
|  | Testing Strategy |  | FALSE |  | 10
|  | Performance KPIs |  | FALSE |  | 10
|  | Customer Deployment/Release policies |  | FALSE |  | 10
| Application Architecture | Requirements Documentation |  | FALSE |  | 25 |  | Solution Review Board established and meeting cadence set |  | FALSE |  | 25
|  | High Level Solution Design |  | FALSE |  | 20 |  | Solution sign off and accpetance process |  | FALSE |  | 30
|  | Architecture Draft |  | FALSE |  | 10 |  | Align Business and Performance KPIs |  | FALSE |  | 20
|  | Hardware Estimates |  | FALSE |  | 10 |  | Risk Assessment |  | FALSE |  | 30
|  | Performance KPIs |  | FALSE |  | 20
|  | Roles and Rights Concept |  | FALSE |  | 10
|  | Special functionality concept |  | FALSE |  | 10
| System Integration | Third party system for integration |  | FALSE |  | 10 |  | Risk Assessment |  | FALSE |  | 30
|  | Stakeholders |  | FALSE |  | 20 |  | SLAs for third party systems |  | FALSE |  | 20
|  | SLAs for third party systems |  | FALSE |  | 20 |  | Third party systems access enabled |  | FALSE |  | 20
| Test Concept | Initial Experience Designs |  | FALSE |  | 10 |  | Testing Strategy |  | FALSE |  | 25
|  | Requirements Documentation |  | FALSE |  | 25 |  | Testing Plans |  | FALSE |  | 20
|  | High Level Solution Design |  | FALSE |  | 20
|  | Use cases |  | FALSE |  | 25
| Support Setup | Setup Support processes |  | FALSE |  | 15 |  | Support processes and access to Adobe Support Portal |  | FALSE |  | 10
|  | List of users that require access to Adobe Support Portal |  | FALSE |  | 10 |  | Escalation Processes |  | FALSE |  | 20
|  | Request for setting up project section in Adobe Support portal |  | FALSE |  | 10 |  | Adobe Support Portal project set up |  | FALSE |  | 10
|  | Escalation Processes |  | FALSE |  | 10
|  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0
Operations & Operations Planning | Permissions | Roles and Rights Concept |  | FALSE |  | 20 |  | Roles and Rights Concept meets security guidelines |  | FALSE |  | 30
| Monitoring & Maintenance | Monitoring Concept |  | FALSE |  | 25 |  | Monitoring Policy communicated to System Engineer |  | FALSE |  | 20
[8 empty] | Monitoring Reports structure in place |  | FALSE |  | 15
| Recovery Plan | Customer Backup and restore policy |  | FALSE |  | 20 |  | Back up and Restore tested |  | FALSE |  | 20
|  | Back up and Restore Concept |  | FALSE |  | 15
|  | Operations Manual |  | FALSE |  | 20
|  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0
Development | Development Environment | List of standard development tools to be used in the project |  | FALSE |  | 10 |  | Document development environment set up |  | FALSE |  | 10
|  | High Level Solution Design |  | FALSE |  | 20 |  | Devolpment environment ready |  | FALSE |  | 10
|  | Architecture Draft |  | FALSE |  | 20
| Test System | High Level Solution Design |  | FALSE |  | 20 |  | Document test environment set up |  | FALSE |  | 10
|  | Architecture Draft |  | FALSE |  | 20 |  | Test environment ready |  | FALSE |  | 10
[8 empty] | Access to test system coordinated |  | FALSE |  | 10
| Production System | System Architecture Definition |  | FALSE |  | 20 |  | Document Production environment set up |  | FALSE |  | 20
|  | Test Reports |  | FALSE |  | 15 |  | Production environment ready |  | FALSE |  | 10
[8 empty] | Align Business and Performance KPIs |  | FALSE |  | 15
| Migration | Current Content Structure and Format |  | FALSE |  | 25 |  | Migration Plan |  | FALSE |  | 25
|  | Legacy System |  | FALSE |  | 10
|  | Migration Strategy |  | FALSE |  | 20
| Documentation | Customizations that affect upgrades documented and hotfixes documented |  | FALSE |  | 15 |  | Communicate Operations Manual |  | FALSE |  | 15
|  | Operational tasks documentation |  | FALSE |  | 20 |  | Communicate Release Notes |  | FALSE |  | 20
|  | Release Notes |  | FALSE |  | 15
|  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0
Performance & Testing | (End-) user Acceptance Test | Release running on production environment |  | FALSE |  | 25 |  | Functionality of the solution are accepted by stakeholders |  | FALSE |  | 30
|  | Acceptance test |  | FALSE |  | 20 |  | Daily UAT Report |  | FALSE |  | 15
|  | Success criteria and definition |  | FALSE |  | 15
| Performance and Load-Test | Performance KPIs |  | FALSE |  | 20 |  | Test Content |  | FALSE |  | 20
|  | Use cases |  | FALSE |  | 15 |  | Communicate Preformance Test Report |  | FALSE |  | 10
|  | Testing Concept |  | FALSE |  | 10 |  | Acceptance from Business Stakeholders |  | FALSE |  | 30
|  | Performance Benchmark |  | FALSE |  | 25
|  | Performance Test Report |  | FALSE |  | 20
|  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0
Rollout | Training | AEM Admin trainings |  | FALSE |  | 10 |  | Communicate training materials and user guides |  | FALSE |  | 10
|  | Training Materials |  | FALSE |  | 20 |  | Appropriately trained staff |  | FALSE |  | 10
|  | User Guides |  | FALSE |  | 20
|  | AEM Author trainings |  | FALSE |  | 15
| Pen Test / Security Test | Customer Security Policies |  | FALSE |  | 25 |  | Business sign off on any required adjustments to the solution or architecture identified and aligned against ROI and KPI expectations |  | FALSE |  | 20
|  | Security issues listed and assesed |  | FALSE |  | 25 |  | Security sign off from business stakeholders |  | FALSE |  | 25
|  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0
Go-Live | Security | Security Checklist |  | FALSE |  | 30 |  | Default security enabled |  | FALSE |  | 20
|  | Security issues listed and assesed |  | FALSE |  | 20 |  | Penetration Test Results |  | FALSE |  | 30
|  | Penetration Test |  | FALSE |  | 20 |  | Penetration Test passed |  | FALSE |  | 35
| Fallback | Fallback system and procedure |  | FALSE |  | 30 |  | Fallback system sign off from business stakeholders |  | FALSE |  | 20
|  | Fallback system and procedure tested |  | FALSE |  | 20
| Support | Go live Schedule |  | FALSE |  | 15 |  | Resources available to support go live |  | FALSE |  | 20
[8 empty] | Inform Adobe Support about the Go live Schedule |  | FALSE |  | 10
| Transition | Deployment / Release Policies and Processes |  | FALSE |  | 20 |  | Production Sign off from business stakeholders |  | FALSE |  | 25
|  | Production Sign off Process and Policy |  | FALSE |  | 25 |  | Release Coordinated |  | FALSE |  | 10
|  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0

## Architect
Phase | Milestone | Required Documents | Y/N |  |  | W | Quality 1-3 | Deliverables | Y/N |  |  | W
Preparation | Validation | Customer Roadmap |  | FALSE |  | 5 |  | High Level Solution Design |  | FALSE |  | 25
|  | ROI expectations |  | FALSE |  | 5 |  | Architecture Draft |  | FALSE |  | 25
|  | Project Scope Document |  | FALSE |  | 10 |  | Hardware Estimates |  | FALSE |  | 25
|  | External System & User dependencies / System Context |  | FALSE |  | 10 |  | Performance KPIs |  | FALSE |  | 25
|  | Existing Systems Map |  | FALSE |  | 10
|  | Experience Designs Requirements |  | FALSE |  | 5
|  | Business Requirements Documentation |  | FALSE |  | 15
|  | Technical Requirements |  | FALSE |  | 20
|  | Customer Security Policies |  | FALSE |  | 10
|  | Security Concept |  | FALSE |  | 10
|  | Historical performance and historical performance KPIs |  | FALSE |  | 10
|  | Success criteria and definition |  | FALSE |  | 10
|  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0
Planning | Handover | Historical performance and historical performance KPIs |  | FALSE |  | 20 |  | Performance KPIs |  | FALSE |  | 35
|  | ROI expectations |  | FALSE |  | 5 |  | Proof of Concept (POC) |  | FALSE |  | 45
|  | Initial Experience Designs |  | FALSE |  | 5 |  | Project efforts initial estimates |  | FALSE |  | 20
|  | Business Requirements Documentation |  | FALSE |  | 20
|  | Technical Requirements |  | FALSE |  | 20
|  | High Level Solution Design |  | FALSE |  | 20
|  | Architecture Draft |  | FALSE |  | 15
|  | Hardware Estimates |  | FALSE |  | 15
| Risk Assessment | Risk Assessment |  | FALSE |  | 30 |  | Technical risk factors verified |  | FALSE |  | 20
|  | Identify critical key solutions/functionalities |  | FALSE |  | 30 |  | Business sign off on any required adjustments to the solution or architecture identified and aligned against ROI and KPI expectations |  | FALSE |  | 25
|  | Technical Requirements |  | FALSE |  | 20 |  | POC tested and verified against Requirement Documentation |  | FALSE |  | 30
|  | Proof of Concept (POC) |  | FALSE |  | 20 |  | Risk Mitigation Plan |  | FALSE |  | 35
|  | System risk factors identified and verified |  | FALSE |  | 25
| Kick Off | Customer Roadmap |  | FALSE |  | 5 |  | Understands scope of project and expectations |  | FALSE |  | 20
|  | Project Scope Document |  | FALSE |  | 5 |  | Hardware will be available to fullfil requirements |  | FALSE |  | 30
|  | ROI expectations |  | FALSE |  | 5 |  | Agreement on KPI's, defined as goals for the project |  | FALSE |  | 30
|  | Initial Experience Designs |  | FALSE |  | 5 |  | Stakeholders |  | FALSE |  | 20
|  | Requirements Documentation |  | FALSE |  | 10 |  | Aware of communication plan |  | FALSE |  | 10
|  | High Level Solution Design |  | FALSE |  | 20 |  | Aware of success definitions and criteria |  | FALSE |  | 15
|  | Architecture Draft |  | FALSE |  | 20
|  | Hardware Estimates |  | FALSE |  | 10
|  | Performance KPIs |  | FALSE |  | 10
|  | Timeline and Milestones |  | FALSE |  | 5
|  | Stakeholders |  | FALSE |  | 5
|  | Success criteria and definition |  | FALSE |  | 15
|  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0
Development Preparation | Development Team trained / Staffing | AEM technical trainings |  | FALSE |  | 15 |  | AEM Certified |  | FALSE |  | 55
|  | AEM Certification Exam |  | FALSE |  | 40 |  | Coding Guidelines |  | FALSE |  | 45
|  | Development Methodology |  | FALSE |  | 15
|  | Customer Coding Guidelines |  | FALSE |  | 30
| Content Architecture | Historical Content Structure |  | FALSE |  | 35 |  | Content Architecture Document |  | FALSE |  | 40
|  | Requirements Documentation |  | FALSE |  | 25 |  | Feasability confirmation on KPI's |  | FALSE |  | 30
|  | High Level Solution Design |  | FALSE |  | 15 |  | Roles and Rights Concept |  | FALSE |  | 30
|  | Architecture Draft |  | FALSE |  | 15
|  | Performance KPIs |  | FALSE |  | 10
| System Architecture | Requirements Documentation |  | FALSE |  | 15 |  | System Architecture Definition |  | FALSE |  | 25
|  | High Level Solution Design |  | FALSE |  | 25 |  | Performance Benchmark |  | FALSE |  | 15
|  | Architecture Draft |  | FALSE |  | 20 |  | Architecture Diagram |  | FALSE |  | 15
|  | Hardware Estimates |  | FALSE |  | 10 |  | Architecture Review Board Sign Off |  | FALSE |  | 20
|  | Performance KPIs |  | FALSE |  | 10 |  | Caching Strategy |  | FALSE |  | 10
|  | Security Architecture Recommendations |  | FALSE |  | 30 |  | Performance and scalability concept |  | FALSE |  | 15
|  | Testing Strategy |  | FALSE |  | 10
|  | Test Suite |  | FALSE |  | 5
|  | Customer Reporting Policies or Requirements |  | FALSE |  | 5
| Application Architecture | Requirements Documentation |  | FALSE |  | 25 |  | Application Architecture Definition |  | FALSE |  | 20
|  | High Level Solution Design |  | FALSE |  | 15 |  | Performance Benchmark |  | FALSE |  | 15
|  | Architecture Diagram |  | FALSE |  | 15 |  | Implementation Concept |  | FALSE |  | 15
|  | Hardware Estimates |  | FALSE |  | 10 |  | Components and templates realtionship concept |  | FALSE |  | 10
|  | Performance KPIs |  | FALSE |  | 10 |  | Workflows concept |  | FALSE |  | 10
|  | Roles and Rights Concept |  | FALSE |  | 10 |  | Security Concept |  | FALSE |  | 20
|  | Coding Guidelines |  | FALSE |  | 5 |  | Mocking Concept of external Interfaces |  | FALSE |  | 10
|  | Special functionality concept |  | FALSE |  | 10
|  | Requirements Documentation |  | FALSE |  | 15
|  | Risk Assessment |  | FALSE |  | 10
| System Integration | Third party system for integration |  | FALSE |  | 30 |  | Third party integration concept |  | FALSE |  | 50
|  | Technical Specification |  | FALSE |  | 20
|  | Risk Assessment |  | FALSE |  | 35
|  | SLAs for third party systems |  | FALSE |  | 15
|  |  | 0% | 0 | 0 |  |  |  |  | 0 | 0
Operations & Operations Planning | Monitoring and Maintenance | Workflow Specification |  | FALSE |  | 10 |  | Purge Rules |  | FALSE |  | 10
|  | Monitoring Points in the application defined |  | FALSE |  | 15 |  | Monitoring Concept |  | FALSE |  | 20
|  | Customer Monitoring Policies or Requirements |  | FALSE |  | 20 |  | Respository Optimization |  | FALSE |  | 20
|  | Monitoring - Security Points |  | FALSE |  | 15
|  | Architecture Review Board Sign Off |  | FALSE |  | 15
|  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0
Development | Production System | System Architecture Definition |  | FALSE |  | 50 |  | Align Business and Performance KPIs |  | FALSE |  | 50
|  | Performance Benchmark |  | FALSE |  | 50
| Integration | Integration Testing |  | FALSE |  | 30 |  | Automation Strategy |  | FALSE |  | 50
|  | Development Role Definition |  | FALSE |  | 30
|  | Current Content Structure and Format |  | FALSE |  | 35
| Migration | Legacy System |  | FALSE |  | 45 |  | Content Architecture Document |  | FALSE |  | 50
|  | Migration Strategy |  | FALSE |  | 45 |  | Duration and frequency estimate |  | FALSE |  | 50
| Communication | System Architecture Definition |  | FALSE |  | 45 |  | Solution Runbook |  | FALSE |  | 55
|  | High Level Solution Design |  | FALSE |  | 35 |  | Deployment / Release Policies and Processes |  | FALSE |  | 45
|  | Architecture Diagram |  | FALSE |  | 20
|  |  | 0% | 0 | 0 |  |  |  |  | 0 | 0
Performance & Testing | Performance and Load-Test | Performance KPIs |  | FALSE |  | 30 |  | Performance Test Results match Performance KPIs |  | FALSE |  | 40
|  | Use cases |  | FALSE |  | 10 |  | Performance Test Report |  | FALSE |  | 30
|  | Test Content |  | FALSE |  | 15 |  | Threshold definition |  | FALSE |  | 15
|  | Testing Concept |  | FALSE |  | 20 |  | Durabilty Test |  | FALSE |  | 15
|  | Test Suite |  | FALSE |  | 5
|  | Caching Strategy |  | FALSE |  | 15
|  | Performance Benchmark |  | FALSE |  | 20
|  |  | 0% | 0 | 0 |  |  |  |  | 0 | 0
Rollout | Pen Test / Security Test | Security Checklist |  | FALSE |  | 45 |  | Security issues listed and assesed |  | FALSE |  | 30
|  | System Architecture Definition |  | FALSE |  | 25 |  | Business sign off on any required adjustments to the solution or architecture identified and aligned against ROI and KPI expectations |  | FALSE |  | 40
|  | White box test results |  | FALSE |  | 30 |  | Penetration Test passed |  | FALSE |  | 50
|  |  | 0% | 0 | 0 |  |  |  |  | 0 | 0
Go Live | Preparation | Content Architecture Document |  | FALSE |  | 50 |  | URL handling concept |  | FALSE |  | 30
|  | Historical Content Structure |  | FALSE |  | 50 |  | Default security enabled |  | FALSE |  | 15
| Security | Security Checklist |  | FALSE |  | 10 |  | Security sign off from business stakeholders |  | FALSE |  | 20
|  | Security issues listed and assesed |  | FALSE |  | 15 |  | Penetration Test passed |  | FALSE |  | 15
|  | Penetration Test Results |  | FALSE |  | 15
| Fallback | Fallback system and procedure |  | FALSE |  | 20 |  | Fallback system sign off from business stakeholders |  | FALSE |  | 40
|  | Fallback system and procedure tested |  | FALSE |  | 20
| Transition | Customer Monitoring Policies or Requirements |  | FALSE |  | 10 |  | Monitoring Concept |  | FALSE |  | 20
|  | Deployment / Release Policies and Processes |  | FALSE |  | 5 |  | Back up and Restore Concept |  | FALSE |  | 10
|  | Production Sign off Process and Policy |  | FALSE |  | 5
|  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0

## Business Analyst
Phase | Milestone | Required Documents | Y/N |  |  |  | Quality 1-3 | Deliverables | Y/N
Preparation | Validation | Customer Roadmap |  | FALSE |  | 5 |  | High Level Solution Design |  | FALSE |  | 25
|  | Project Scope Document |  | FALSE |  | 15 |  | Requirements Documentation |  | FALSE |  | 5
|  | ROI expectations |  | FALSE |  | 10
|  | Experience Designs Requirements |  | FALSE |  | 15
|  | Business Requirements Documentation |  | FALSE |  | 20
|  | Technical Requirements |  | FALSE |  | 20
|  | Success criteria and definition |  | FALSE |  | 15
|  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0
Planning | Handover | Customer Roadmap |  | FALSE |  | 5 |  | Performance KPIs |  | FALSE |  | 25
|  | ROI expectations |  | FALSE |  | 10 |  | Business KPIs |  | FALSE |  | 25
|  | Business KPIs |  | FALSE |  | 25 |  | Business Analyst understands scope of project and expectations |  | FALSE |  | 10
|  | Initial Experience Designs |  | FALSE |  | 20
|  | High Level Solution Design |  | FALSE |  | 20
|  | Architecture Draft |  | FALSE |  | 10
|  | Historical performance and historical performance KPIs |  | FALSE |  | 20
| Risk Assessment | Risk Assessment |  | FALSE |  | 10 |  | Technical risk factors verified |  | FALSE |  | 10
|  | Identify critical key solutions/functionalities |  | FALSE |  | 15 |  | Business sign off on any required adjustments to the solution or architecture identified and aligned against ROI and KPI expectations |  | FALSE |  | 20
| Communication | Stakeholders |  | FALSE |  | 10 |  | Specification review and approval process defined and communicated |  | FALSE |  | 20
|  | Issue tracking system and processes |  | FALSE |  | 15 |  | Solution Review Board established and meeting cadence set |  | FALSE |  | 30
|  | Customer Specification Guidelines |  | FALSE |  | 20
| Kick Off | Customer Roadmap |  | FALSE |  | 10 |  | Understands scope of project and expectations |  | FALSE |  | 15
|  | Project Scope Document |  | FALSE |  | 10 |  | Agreement on KPI's, defined as goals for the project |  | FALSE |  | 30
|  | ROI expectations |  | FALSE |  | 20 |  | Stakeholders |  | FALSE |  | 20
|  | Initial Experience Designs |  | FALSE |  | 10 |  | Aware of communication plan |  | FALSE |  | 10
|  | Requirements Documentation |  | FALSE |  | 30 |  | Aware of success definitions and criteria |  | FALSE |  | 15
|  | High Level Solution Design |  | FALSE |  | 15
|  | Architecture Draft |  | FALSE |  | 15
|  | Performance KPIs |  | FALSE |  | 20
|  | Timeline and Milestones |  | FALSE |  | 15
|  | Project Ogranization |  | FALSE |  | 20
|  | Success criteria and definition |  | FALSE |  | 15
|  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0
Development Preparation | Development Team trained / Staffing | AEM technical trainings |  | FALSE |  | 15 |  | AEM Certified |  | FALSE |  | 20
|  | AEM Certification Exam |  | FALSE |  | 20
| Content Architecture | Initial Experience Designs |  | FALSE |  | 10 |  | Content Architecture Document |  | FALSE |  | 25
|  | Requirements Documentation |  | FALSE |  | 20 |  | Roles and Rights Specification |  | FALSE |  | 20
|  | High Level Solution Design |  | FALSE |  | 15
|  | Architecture Draft |  | FALSE |  | 10
|  | Performance KPIs |  | FALSE |  | 20
|  | Roles and Rights Concept |  | FALSE |  | 15
|  | Historical Content Structure |  | FALSE |  | 10
| System Architecture | Requirements Documentation |  | FALSE |  | 10 |  | System Architecture Documentation |  | FALSE |  | 15
|  | High Level Solution Design |  | FALSE |  | 10
|  | Application Architecture Definition |  | FALSE |  | 25
|  | System Architecture Definition |  | FALSE |  | 20
| Application Architecture | Requirements Documentation |  | FALSE |  | 10 |  | Components Specification |  | FALSE |  | 25
|  | Components and templates realtionship concept |  | FALSE |  | 20 |  | Template Specification |  | FALSE |  | 25
|  | Special functionality concept |  | FALSE |  | 20 |  | Components and Templates relationship Specification |  | FALSE |  | 20
|  | Performance KPIs |  | FALSE |  | 15 |  | Special Functionality Specification |  | FALSE |  | 20
|  | Workflows concept |  | FALSE |  | 20 |  | Workflow Specification |  | FALSE |  | 25
| System Integration | Third party system for integration |  | FALSE |  | 10 |  | Third party integration Specification |  | FALSE |  | 20
|  | Third party integration concept |  | FALSE |  | 15 |  | Dialogs Specification |  | FALSE |  | 20
| Experience Design | Initial Experience Designs |  | FALSE |  | 10 |  | Experience Specifications |  | FALSE |  | 10
|  | Requirements Documentation |  | FALSE |  | 10
|  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0
Development | Documentation | Components Specification |  | FALSE |  | 10 |  | Training Materials |  | FALSE |  | 30
|  | Template Specification |  | FALSE |  | 10 |  | User Guides |  | FALSE |  | 30
|  | Components and Templates relationship Specification |  | FALSE |  | 10
|  | Special Functionality Specification |  | FALSE |  | 10
|  | Third party integration Specification |  | FALSE |  | 10
|  | Experience Specifications |  | FALSE |  | 10
|  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0

## Development Lead
Phase | Milestone | Required Documents | Y/N |  |  |  | Quality 1-3 | Deliverables | Y/N
Preparation | Budget | Project Scope Document |  | FALSE |  | 25 |  | Project efforts initial estimates |  | FALSE |  | 50
|  | High Level Solution Design |  | FALSE |  | 30
|  | Hardware Estimates |  | FALSE |  | 10
|  | Business Requirements Documentation |  | FALSE |  | 40
|  | Technical Requirements |  | FALSE |  | 50
|  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0
Planning | Handover | Proof of Concept (POC) |  | FALSE |  | 40 |  | Performance KPIs |  | FALSE |  | 40
|  | Project Scope Document |  | FALSE |  | 30 |  | Development team understands scope of project and expectations |  | FALSE |  | 30
|  | ROI expectations |  | FALSE |  | 25 |  | Implementation Concept |  | FALSE |  | 50
|  | Experience Designs Requirements |  | FALSE |  | 35
|  | Requirements Documentation |  | FALSE |  | 50
|  | High Level Solution Design |  | FALSE |  | 35
|  | Architecture Draft |  | FALSE |  | 40
|  | Hardware Estimates |  | FALSE |  | 10
|  | Historical performance and historical performance KPIs |  | FALSE |  | 35
| Risk Assessment | Risk Assessment |  | FALSE |  | 40 |  | Technical risk factors verified |  | FALSE |  | 50
|  | Identify critical key solutions/functionalities |  | FALSE |  | 30 |  | Security Concept |  | FALSE |  | 40
|  | Requirements Documentation |  | FALSE |  | 25
|  | Proof of Concept (POC) |  | FALSE |  | 25
|  | Risk Mitigation Plan |  | FALSE |  | 40
| Kick Off | Customer Roadmap |  | FALSE |  | 10 |  | Understands scope of project and expectations |  | FALSE |  | 30
|  | Project Scope Document |  | FALSE |  | 30 |  | Hardware will be available to fullfil requirements |  | FALSE |  | 25
|  | Experience Designs Requirements |  | FALSE |  | 20 |  | Agreement on KPI's, defined as goals for the project |  | FALSE |  | 30
|  | Requirements Documentation |  | FALSE |  | 50 |  | Aware of communication plan |  | FALSE |  | 10
|  | High Level Solution Design |  | FALSE |  | 25 |  | Aware of success definitions and criteria |  | FALSE |  | 40
|  | Architecture Draft |  | FALSE |  | 25 |  | Development Methodology |  | FALSE |  | 50
|  | Timeline and Milestones |  | FALSE |  | 20
|  | Performance KPIs |  | FALSE |  | 40
|  | Success criteria and definition |  | FALSE |  | 30
|  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0
Development Preparation | Development Team trained / Staffing | AEM technical trainings |  | FALSE |  | 40 |  | AEM Certified |  | FALSE |  | 50
|  | AEM Certification Exam |  | FALSE |  | 40
| Content Architecture | Architecture Draft |  | FALSE |  | 30 |  | Implementation - Content Architecture |  | FALSE |  | 50
|  | Experience Specifications |  | FALSE |  | 20 |  | Feasability confirmation on KPI's |  | FALSE |  | 40
|  | Content Architecture Document |  | FALSE |  | 50 |  | Implementation - Roles and Rights |  | FALSE |  | 40
|  | Roles and Rights Concept |  | FALSE |  | 30
|  | Roles and Rights Specification |  | FALSE |  | 40
| Application Architecture | Requirements Documentation |  | FALSE |  | 40 |  | Implementation Concept |  | FALSE |  | 50
|  | Application Architecture Definition |  | FALSE |  | 50 |  | Implementation - Workflows |  | FALSE |  | 40
|  | Performance Benchmark |  | FALSE |  | 40 |  | Caching Strategy |  | FALSE |  | 30
|  | Coding Guidelines |  | FALSE |  | 50 |  | Implementation - Security Software |  | FALSE |  | 40
|  | Security Based Coding Guidelines |  | FALSE |  | 50
|  | Security Concept |  | FALSE |  | 40
|  | Special functionality concept |  | FALSE |  | 30
|  | Components and Templates relationship Specification |  | FALSE |  | 30
|  | Workflow Specification |  | FALSE |  | 25
| System Integration | Third party integration concept |  | FALSE |  | 30 |  | Implementation - Integration |  | FALSE |  | 40
|  | Third party system for integration |  | FALSE |  | 40
|  | Risk Assessment |  | FALSE |  | 20
|  | Technical Specification |  | FALSE |  | 40
| Experience Design | Experience Specifications |  | FALSE |  | 30 |  | Implementation - Experience Design |  | FALSE |  | 30
| Test Concept | Requirements Documentation |  | FALSE |  | 30 |  | Test Content |  | FALSE |  | 40
[8 empty] | Automated Testing Strategy |  | FALSE |  | 30
| Support Setup | Setup Support processes |  | FALSE |  | 30 |  | Support processes and access to Adobe Support Portal |  | FALSE |  | 30
|  | List of users that require access to Adobe Support Portal |  | FALSE |  | 30
|  | Escalation Processes |  | FALSE |  | 20
|  | Adobe Support Portal project set up |  | FALSE |  | 20
|  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0
Operations & Operations Planning | Monitoring & Maintenance | Monitoring Concept |  | FALSE |  | 40 |  | Monitoring Points in the application defined |  | FALSE |  | 5
[8 empty] | Log File Analysis |  | FALSE |  | 5
[8 empty] | Error Handling Concept |  | FALSE |  | 5
[8 empty] | Error Handling Documentation |  | FALSE |  | 5
[8 empty] | Application specific maintenance tasks defined |  | FALSE |  | 5
|  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0
Development | Development Environment | Devolpment environment ready |  | FALSE |  | 40 |  | List of standard development tools to be used in the project |  | FALSE |  | 30
|  | High Level Solution Design |  | FALSE |  | 30 |  | Software Architecture Startegy |  | FALSE |  | 40
|  | Architecture Draft |  | FALSE |  | 25 |  | Deployment cadence establiished |  | FALSE |  | 20
|  | Automation Strategy |  | FALSE |  | 25 |  | Development Role Definition |  | FALSE |  | 20
| Production System | Production environment ready |  | FALSE |  | 50 |  | Pre-Deployment Checklist |  | FALSE |  | 30
|  | Deployment / Release Policies and Processes |  | FALSE |  | 30 |  | Package Prepared |  | FALSE |  | 50
| Migration | Current Content Structure and Format |  | FALSE |  | 25 |  | Implementation - Migration Strategy |  | FALSE |  | 40
|  | Legacy System |  | FALSE |  | 30
|  | Migration Strategy |  | FALSE |  | 35
| Documentation | Customizations that affect upgrades documented and hotfixes documented |  | FALSE |  | 30 |  | Release Notes |  | FALSE |  | 40
|  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0
Performance & Testing | (End-) user Acceptance Test | Release running on prod |  | FALSE |  | 50 |  | Functionality of the solution are accepted by stakeholders |  | FALSE |  | 50
|  | Acceptance test |  | FALSE |  | 40 |  | Post-Deployment Checklist |  | FALSE |  | 40
| Performance and Load-Test | Performance Test Report |  | FALSE |  | 40 |  | Use cases |  | FALSE |  | 30
|  | Requirements Documentation |  | FALSE |  | 30
|  | Performance KPIs |  | FALSE |  | 50
|  | Caching Strategy |  | FALSE |  | 20
|  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0
Rollout | Pen Test / Security Test | Security issues listed and assesed |  | FALSE |  | 40 |  | Implementation - Any needed changes based on Penetration Test Results |  | FALSE |  | 50
|  | System Architecture Documentation |  | FALSE |  | 30
|  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0
Go-Live | Preparation | URL handling concept |  | FALSE |  | 30 |  | Initial Experience Designs |  | FALSE |  | 50
|  | Default security enabled |  | FALSE |  | 40
| Security | Penetration Test Results |  | FALSE |  | 50 |  | Default security enabled |  | FALSE |  | 40
|  | Security issues listed and assesed |  | FALSE |  | 30 |  | Implementation - Any needed changes based on Penetration Test Results |  | FALSE |  | 50
[8 empty] | Penetration Test passed |  | FALSE |  | 50
[8 empty] | Error Handling Documentation |  | FALSE |  | 30
[8 empty] | Application specific maintenance tasks defined |  | FALSE |  | 30
|  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0

## Quality Lead
Phase | Milestone | Required Documents | Y/N |  |  |  | Quality 1-3 | Deliverables | Y/N
Preparation | Validation | Customer Roadmap |  | FALSE |  | 10 |  | Project efforts initial estimates |  | FALSE |  | 50
|  | Project Scope Document |  | FALSE |  | 25 |  | Testing Scope |  | FALSE |  | 30
|  | ROI expectations |  | FALSE |  | 10
|  | Experience Designs Requirements |  | FALSE |  | 25
|  | Business Requirements Documentation |  | FALSE |  | 30
|  | Technical Requirements |  | FALSE |  | 30
|  | Success criteria and definition |  | FALSE |  | 25
|  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0
Planning | Handover | Performance KPIs |  | FALSE |  | 20 |  | Testing Strategy |  | FALSE |  | 40
|  | Business KPIs |  | FALSE |  | 10 |  | Testing Plans |  | FALSE |  | 30
|  | Business Requirements Documentation |  | FALSE |  | 30 |  | Understands scope of project and expectations |  | FALSE |  | 20
|  | Technical Requirements |  | FALSE |  | 30
|  | Success criteria and definition |  | FALSE |  | 25
| Communication | Stakeholders |  | FALSE |  | 10 |  | Quality report format and cadence |  | FALSE |  | 40
|  | Issue tracking process |  | FALSE |  | 30 |  | Establish regular quality review sessions |  | FALSE |  | 30
|  | Project communication plan |  | FALSE |  | 20
| Kick Off | Customer Roadmap |  | FALSE |  | 10 |  | Understands scope of project and expectations |  | FALSE |  | 20
|  | Project Scope Document |  | FALSE |  | 25 |  | Agreement on KPI's, defined as goals for the project |  | FALSE |  | 30
|  | ROI expectations |  | FALSE |  | 10 |  | Stakeholders |  | FALSE |  | 10
|  | Experience Designs Requirements |  | FALSE |  | 25 |  | Aware of communication plan |  | FALSE |  | 10
|  | Requirements Documentation |  | FALSE |  | 40 |  | Aware of success definitions and criteria |  | FALSE |  | 20
|  | High Level Solution Design |  | FALSE |  | 30
|  | Architecture Draft |  | FALSE |  | 20
|  | Performance KPIs |  | FALSE |  | 30
|  | Timeline and Milestones |  | FALSE |  | 25
|  | Project Ogranization |  | FALSE |  | 10
|  | Success criteria and definition |  | FALSE |  | 25
|  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0
Development Preparation | Development Team trained / Staffing | AEM technical trainings |  | FALSE |  | 30 |  | AEM Certified |  | FALSE |  | 50
|  | AEM Certification Exam |  | FALSE |  | 40
| Content Architecture | Content Architecture Document |  | FALSE |  | 20 |  | Testing Strategy |  | FALSE |  | 40
|  | Requirements Documentation |  | FALSE |  | 40 |  | Testing Strategy |  | FALSE |  | 20
|  | Performance KPIs |  | FALSE |  | 25
| System Integration | Third party system for integration |  | FALSE |  | 30 |  | Thirday party Testing Concept |  | FALSE |  | 30
|  | Third party integration concept |  | FALSE |  | 20 |  | Third party systems access enabled |  | FALSE |  | 30
|  | Third party security concept |  | FALSE |  | 20
|  | Third party integration Specification |  | FALSE |  | 25
| Test Concept | Requirements Documentation |  | FALSE |  | 40 |  | Test tooling suite selected |  | FALSE |  | 30
|  | Components and templates realtionship concept |  | FALSE |  | 30 |  | Automated Testing Strategy |  | FALSE |  | 20
|  | Special Functionality Specification |  | FALSE |  | 25 |  | Testing Concept |  | FALSE |  | 25
|  | Performance KPIs |  | FALSE |  | 30 |  | Use Cases converted into test scenarios |  | FALSE |  | 30
|  | Workflow Specification |  | FALSE |  | 20 |  | Happy Paths defined |  | FALSE |  | 20
|  | Testing Strategy |  | FALSE |  | 20 |  | Smoke Test Concept |  | FALSE |  | 40
|  | Testing Plans |  | FALSE |  | 30 |  | Persona based Testing Concept |  | FALSE |  | 20
|  | Use cases |  | FALSE |  | 30 |  | Integration Testing |  | FALSE |  | 25
|  | Development Methodology |  | FALSE |  | 15
|  | Third party integration Specification |  | FALSE |  | 30
|  | Roles and Rights Specification |  | FALSE |  | 20
|  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0
Development | Test System | Test environment ready |  | FALSE |  | 40 |  | Test Suite |  | FALSE |  | 25
|  | Automated Testing Strategy |  | FALSE |  | 30 |  | implementation - Automated Testing Strategy |  | FALSE |  | 20
|  | Architecture Draft |  | FALSE |  | 20
| Production System | Production environment ready |  | FALSE |  | 30 |  | Smoke Tests executed for system validation |  | FALSE |  | 40
|  | Third party systems access enabled |  | FALSE |  | 30
| Integration | Integration Testing |  | FALSE |  | 25 |  | implementation - Automated Testing Strategy |  | FALSE |  | 40
|  | Development Role Definition |  | FALSE |  | 20
| Documentation | Issue tracking system and processes |  | FALSE |  | 25 |  | Test Reports |  | FALSE |  | 40
|  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0
Performance & Testing | (End-) user Acceptance Test | Customer Test Reports |  | FALSE |  | 40 |  | Support in validation of reported issues |  | FALSE |  | 40
| Performance and Load-Test | Performance and scalability concept |  | FALSE |  | 40 |  | Test Reports |  | FALSE |  | 20
|  | Performance KPIs |  | FALSE |  | 20 |  | Automated Testing Strategy validated against realistic and expected load |  | FALSE |  | 25
|  | Test Content |  | FALSE |  | 30 |  | Automated test suite adapted to real content and results compared to KPIs |  | FALSE |  | 30
|  | Testing Concept |  | FALSE |  | 20 |  | Testing Concept |  | FALSE |  | 20
|  | Test Suite |  | FALSE |  | 20 |  | Acceptance from Business Stakeholders |  | FALSE |  | 40
|  | Automated Testing Strategy |  | FALSE |  | 10 |  | Penetration Test Results |  | FALSE |  | 30
|  | Use cases |  | FALSE |  | 20 |  | Durability Test Results |  | FALSE |  | 30
|  | Durabilty Test |  | FALSE |  | 20
|  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0
Go-Live | Roll Out | Smoke Test Concept |  | FALSE |  | 40 |  | Smoke Tests executed for system validation |  | FALSE |  | 25
|  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0

## System Engineer
Phase | Milestone | Required Documents | Y/N |  |  |  | Quality 1-3 | Deliverables | Y/N
Preparation | Validation | External System & User dependencies / System Context |  | FALSE |  | 30 |  | High Level System Map |  | FALSE |  | 30
|  | Experience Designs Requirements |  | FALSE |  | 10 |  | Hardware Estimates |  | FALSE |  | 40
|  | Business Requirements Documentation |  | FALSE |  | 25
|  | Technical Requirements |  | FALSE |  | 25
|  | Customer Security Policies |  | FALSE |  | 30
|  | Security Concept |  | FALSE |  | 30
|  | Historical performance and historical performance KPIs |  | FALSE |  | 20
|  | Performance KPIs |  | FALSE |  | 40
|  | Architecture Draft |  | FALSE |  | 40
|  | Existing Systems Map |  | FALSE |  | 20
|  | Success criteria and definition |  | FALSE |  | 10
|  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0
Planning | Handover | ROI expectations |  | FALSE |  | 20 |  | Proof of Concept (POC) |  | FALSE |  | 40
|  | Experience Designs Requirements |  | FALSE |  | 10 |  | Project efforts initial estimates |  | FALSE |  | 30
|  | Requirements Documentation |  | FALSE |  | 30
|  | High Level Solution Design |  | FALSE |  | 20
|  | Architecture Draft |  | FALSE |  | 30
|  | Hardware Estimates |  | FALSE |  | 30
|  | Performance KPIs |  | FALSE |  | 40
| Risk Assessment | Risk Assessment |  | FALSE |  | 35 |  | System risk factors identified and verified |  | FALSE |  | 35
|  | Identify critical key solutions/functionalities |  | FALSE |  | 30 |  | Business sign off on any required adjustments to the solution or architecture identified and aligned against ROI and KPI expectations |  | FALSE |  | 20
|  | Requirements Documentation |  | FALSE |  | 20 |  | POC tested and verified against Requirement Documentation |  | FALSE |  | 40
|  | Proof of Concept (POC) |  | FALSE |  | 35 |  | Risk Mitigation Plan |  | FALSE |  | 30
| Communication | Customer Deployment/Release policies |  | FALSE |  | 25 |  | Deployment / Release Policies and Processes |  | FALSE |  | 40
|  | Customer Reporting Policies or Requirements |  | FALSE |  | 30 |  | Pre-Deployment Checklist |  | FALSE |  | 40
|  | Timeline and Milestones |  | FALSE |  | 30 |  | Post-Deployment Checklist |  | FALSE |  | 40
| Kick Off | Project Scope Document |  | FALSE |  | 20 |  | Understands scope of project and expectations |  | FALSE |  | 20
|  | ROI expectations |  | FALSE |  | 10 |  | Hardware will be available to fullfil requirements |  | FALSE |  | 50
|  | Experience Designs Requirements |  | FALSE |  | 10 |  | Agreement on KPI's, defined as goals for the project |  | FALSE |  | 20
|  | Requirements Documentation |  | FALSE |  | 30 |  | Aware of communication plan |  | FALSE |  | 10
|  | High Level Solution Design |  | FALSE |  | 20 |  | Aware of success definitions and criteria |  | FALSE |  | 20
|  | Architecture Draft |  | FALSE |  | 35
|  | Hardware Estimates |  | FALSE |  | 30
|  | Performance KPIs |  | FALSE |  | 40
|  | Timeline and Milestones |  | FALSE |  | 20
|  | Deployment / Release Policies and Processes |  | FALSE |  | 30
|  | Success criteria and definition |  | FALSE |  | 20
|  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0
Development Preparation | Development Team trained / Staffing | AEM technical trainings |  | FALSE |  | 30 |  | AEM Certified |  | FALSE |  | 50
|  | AEM Certification Exam |  | FALSE |  | 40
| System Architecture | Requirements Documentation |  | FALSE |  | 30 |  | System Architecture Definition |  | FALSE |  | 30
|  | High Level Solution Design |  | FALSE |  | 40 |  | Deployment / Release Policies and Processes |  | FALSE |  | 20
|  | Architecture Draft |  | FALSE |  | 20 |  | Automation Strategy |  | FALSE |  | 25
|  | Hardware Estimates |  | FALSE |  | 30
|  | Performance KPIs |  | FALSE |  | 20
|  | Security Architecture Recommendations |  | FALSE |  | 30
|  | Testing Strategy |  | FALSE |  | 20
|  | Customer Deployment/Release policies |  | FALSE |  | 25
| System Integration | Third party system for integration |  | FALSE |  | 35 |  | Third party integration concept |  | FALSE |  | 30
|  | Technical Specification |  | FALSE |  | 30 |  | Third party systems access enabled |  | FALSE |  | 20
| Support Setup | Escalation Processes |  | FALSE |  | 20 |  | Adobe Support Portal project set up |  | FALSE |  | 40
|  | Deployment / Release Policies and Processes |  | FALSE |  | 40 |  | Support processes and access to Adobe Support Portal |  | FALSE |  | 35
|  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0
Operations & Operations Planning | Permissions | Roles and Rights Concept |  | FALSE |  | 50 |  | Implementation - Roles and Rights |  | FALSE |  | 50
| Monitoring & Maintenance | Purge Rules |  | FALSE |  | 30 |  | Operations Manual |  | FALSE |  | 35
|  | Monitoring Concept |  | FALSE |  | 30 |  | Monitoring - System |  | FALSE |  | 25
|  | Respository Optimization |  | FALSE |  | 20 |  | Monitoring - Threshold and interventation |  | FALSE |  | 25
|  | Threshold definition |  | FALSE |  | 25 |  | Monitoring - External system |  | FALSE |  | 25
|  | Operational tasks documentation |  | FALSE |  | 35 |  | Monitoring - Disk space |  | FALSE |  | 25
|  | Third party security concept |  | FALSE |  | 35 |  | Monitoring - CPU |  | FALSE |  | 25
|  | Third party integration concept |  | FALSE |  | 25 |  | Monitoring - Disk I/O |  | FALSE |  | 25
[8 empty] | Monitoring - Network Bandwith |  | FALSE |  | 25
[8 empty] | Monitoring - Requests |  | FALSE |  | 25
[8 empty] | Monitoring - System |  | FALSE |  | 35
[8 empty] | Maintenance tasks specific to AEM tested and enabled |  | FALSE |  | 30
[8 empty] | Monitoring Reports structure in place |  | FALSE |  | 20
| Recovery Plan | Customer Backup and restore policy |  | FALSE |  | 30 |  | Back up and Restore tested |  | FALSE |  | 40
|  | Operations Manual |  | FALSE |  | 35 |  | Back up and Restore Concept |  | FALSE |  | 50
|  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0
Development | Development Environment | System Architecture Definition |  | FALSE |  | 30 |  | Document development environment set up |  | FALSE |  | 25
|  | Test Suite |  | FALSE |  | 20 |  | Devolpment environment ready |  | FALSE |  | 40
| Test System | Third party integration concept |  | FALSE |  | 30 |  | Document test environment set up |  | FALSE |  | 25
|  | System Architecture Definition |  | FALSE |  | 40 |  | Test environment ready |  | FALSE |  | 40
|  | Performance KPIs |  | FALSE |  | 30
|  | Proof of Concept (POC) |  | FALSE |  | 20
|  | Success criteria and definition |  | FALSE |  | 10
| Production System | System Architecture Definition |  | FALSE |  | 20 |  | Production environment ready |  | FALSE |  | 40
|  | Performance KPIs |  | FALSE |  | 30 |  | Production environment baseline performance tests |  | FALSE |  | 30
|  | Success criteria and definition |  | FALSE |  | 10 |  | Performance Test Results match Performance KPIs |  | FALSE |  | 25
|  | Automated Testing Strategy |  | FALSE |  | 25 |  | Implementation - System Architecture Security Concept |  | FALSE |  | 30
|  | System Architecture Security Concept |  | FALSE |  | 25
|  | Test Cases |  | FALSE |  | 10
|  | Caching Strategy |  | FALSE |  | 20
|  | Performance and scalability concept |  | FALSE |  | 25
|  | Automation Strategy |  | FALSE |  | 25
| Integration | Integration Testing |  | FALSE |  | 25 |  | Implementation - Automation Strategy |  | FALSE |  | 25
|  | Use cases |  | FALSE |  | 20
| Documentation | Document required upgrades, hotfixes |  | FALSE |  | 30 |  | Operations Manual |  | FALSE |  | 50
|  | Operational tasks documentation |  | FALSE |  | 25
|  | Release Notes |  | FALSE |  | 40
|  | Customer Security Policies |  | FALSE |  | 20
|  | Customer Backup and restore policy |  | FALSE |  | 20
|  | Roles and Rights Specification |  | FALSE |  | 25
|  |  | 0.028571 | 0 | 0 |  |  |  |  | 0 | 0
Performance & Testing | (End-) user Acceptance Test | Deployment / Release Policies and Processes |  | FALSE |  | 30 |  | Release running on production environment |  | FALSE |  | 50
|  | Automation Strategy |  | FALSE |  | 20
|  | Operations Manual |  | FALSE |  | 20
| Performance and Load-Test | Performance KPIs |  | FALSE |  | 40 |  | Post-Deployment Checklist |  | FALSE |  | 40
|  | Use cases |  | FALSE |  | 20 |  | Durabilty Test Executed |  | FALSE |  | 25
|  | Test Content |  | FALSE |  | 30 |  | Performance Test Results match Performance KPIs |  | FALSE |  | 30
|  | Testing Concept |  | FALSE |  | 25
|  | Durabilty Test |  | FALSE |  | 25
|  | Test Suite |  | FALSE |  | 25
|  | Caching Strategy |  | FALSE |  | 25
|  | Performance Benchmark |  | FALSE |  | 35
|  | Threshold definition |  | FALSE |  | 30
|  | Performance Test Report |  | FALSE |  | 40
|  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0
Rollout | Preparation | URL handling concept |  | FALSE |  | 40 |  | Implementation - URL Handling |  | FALSE |  | 40
| Pen Test | Security Checklist |  | FALSE |  | 50 |  | Implementation - Any needed changes based on Penetration Test Results |  | FALSE |  | 40
|  | Security issues listed and assesed |  | FALSE |  | 20
|  | System Architecture Documentation |  | FALSE |  | 20
|  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0
Go-Live | Security | Security Checklist |  | FALSE |  | 50 |  | Default security enabled |  | FALSE |  | 40
|  | Security issues listed and assesed |  | FALSE |  | 30 |  | Implementation - Security Concept |  | FALSE |  | 50
|  | Penetration Test |  | FALSE |  | 25 |  | Penetration Test Results |  | FALSE |  | 50
| Fallback | Fallback system and procedure |  | FALSE |  | 30 |  | Implementation - Fallback system and procedure |  | FALSE |  | 30
|  | Fallback system and procedure tested |  | FALSE |  | 25
| Support | Go live Schedule |  | FALSE |  | 20 |  | Resources available to support go live |  | FALSE |  | 30
|  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0

## Security Lead
Phase | Milestone | Required Documents | Y/N |  |  |  | Quality 1-3 | Deliverables | Y/N
Planning | Handover | Historical performance and historical performance KPIs |  | FALSE |  | 10 |  | Security Concept Draft |  | FALSE |  | 50
|  | ROI expectations |  | FALSE |  | 20
|  | Experience Designs Requirements |  | FALSE |  | 10
|  | Business Requirements Documentation |  | FALSE |  | 20
|  | Technical Requirements |  | FALSE |  | 30
|  | High Level Solution Design |  | FALSE |  | 25
|  | Architecture Draft |  | FALSE |  | 30
|  | Hardware Estimates |  | FALSE |  | 10
|  | Customer Security Policies |  | FALSE |  | 40
|  | Success criteria and definition |  | FALSE |  | 20
| Risk Assessment | Security Concept |  | FALSE |  | 40 |  | Security Concept |  | FALSE |  | 50
|  | Identify critical key solutions/functionalities |  | FALSE |  | 35 |  | Security Checklist |  | FALSE |  | 40
|  | Requirements Documentation |  | FALSE |  | 25 |  | Adobe Security Checklist |  | FALSE |  | 35
|  | Proof of Concept (POC) |  | FALSE |  | 20
|  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0
Development Preparation | Development Team trained / Staffing | AEM technical trainings |  | FALSE |  | 35 |  | AEM Certified |  | FALSE |  | 50
|  | AEM Certification Exam |  | FALSE |  | 40
| Content Architecture | Roles and Rights Concept |  | FALSE |  | 30 |  | Roles and Rights Specification |  | FALSE |  | 40
|  | Requirements Documentation |  | FALSE |  | 30
|  | High Level Solution Design |  | FALSE |  | 20
|  | Architecture Draft |  | FALSE |  | 20
|  | Content Architecture Document |  | FALSE |  | 20
| System Architecture | Requirements Documentation |  | FALSE |  | 30 |  | Security Architecture Recommendations |  | FALSE |  | 30
|  | High Level Solution Design |  | FALSE |  | 20
|  | Architecture Draft |  | FALSE |  | 20
|  | Hardware Estimates |  | FALSE |  | 20
|  | Performance KPIs |  | FALSE |  | 10
| Application Architecture | Security Concept |  | FALSE |  | 40 |  | Security Based Coding Guidelines |  | FALSE |  | 50
|  | Security Checklist |  | FALSE |  | 50
|  | Adobe Security Checklist |  | FALSE |  | 40
| System Integration | Third party system for integration |  | FALSE |  | 40 |  | Third party system for integration |  | FALSE |  | 50
|  | Third party integration Specification |  | FALSE |  | 30
|  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0
Operations & Operations Planning | Permissions | Roles and Rights Concept |  | FALSE |  | 40 |  | Roles and Rights Concept meets security guidelines |  | FALSE |  | 50
| Monitoring & Maintenance | External System & User dependencies / System Context |  | FALSE |  | 20 |  | Monitoring - Security Points |  | FALSE |  | 35
|  | System Architecture Documentation |  | FALSE |  | 25
| Recovery Plan | Back up and Restore Concept |  | FALSE |  | 30 |  | Compliance to Security Concept |  | FALSE |  | 30
|  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0
Development | Development Environment | Customer Security Policies |  | FALSE |  | 40 |  | Implementation - Security Concept |  | FALSE |  | 50
|  | Security Concept |  | FALSE |  | 50 |  | Compliance to Customer Security Requirements |  | FALSE |  | 40
| Production System | System Architecture Documentation |  | FALSE |  | 20 |  | System Architecture Security Concept |  | FALSE |  | 35
| Documentation | Security Checklist |  | FALSE |  | 35 |  | Operations Manual |  | FALSE |  | 30
|  | Adobe Security Checklist |  | FALSE |  | 35
|  | Customer Security Policies |  | FALSE |  | 40
|  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0
Rollout | Pen Test | Security Checklist |  | FALSE |  | 40 |  | Security issues listed and assesed |  | FALSE |  | 30
|  | Penetration Test Results |  | FALSE |  | 50 |  | Penetration Test passed |  | FALSE |  | 50
|  | System Architecture Documentation |  | FALSE |  | 30
|  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0
Go-Live | Security | Security Checklist |  | FALSE |  | 40 |  | Default security enabled |  | FALSE |  | 30
|  | Security issues listed and assesed |  | FALSE |  | 35 |  | Security sign off from business stakeholders |  | FALSE |  | 50
|  | Adobe Security Checklist |  | FALSE |  | 35 |  | Penetration Test passed |  | FALSE |  | 50
|  | Penetration Test |  | FALSE |  | 45
| Fallback | Fallback system and procedure |  | FALSE |  | 30 |  | Compliance to Customer Security Requirements |  | FALSE |  | 35
|  | System Architecture Security Concept |  | FALSE |  | 35
| Support | Go live Schedule |  | FALSE |  | 20
|  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0

## Glossary
GLOSSARY
| Term | Definition | Adobe Docs Link
A
| Acceptance test | Acceptance testing is a test conducted to determine if the requirements of a specification or contract are met.
| Acceptance from Business Stakeholders | Acceptance from Business Stakeholders ensures that business requirements meet the Business Case and required stakeholders are aligned with the solution and have granted approval.
| Access to test system coordinated | All roles that require access are granted the required level of access to all systems.
| Adobe Security Checklist | Official checklist provided by Adobe that contains the steps to perform to ensure that AEM is secure at installation. | https://experienceleague.adobe.com/docs/experience-manager-65/administering/security/security-checklist.html?lang=en#security
| Adobe Support Portal project set up | The Adobe Support Portal enables implementation partners and customers to set up the AEM implementation as a project in the Support Portal. This will enable transparency between the customer and Adobe as to the technologies and version implemented. | https://experienceleague.adobe.com/docs/customer-one/using/home.html?lang=en
| Agreement on KPI's, defined as goals for the project | KPIs assist an organization to define and measure progress toward organizational goals and objectives. Once an organization has analysed its mission and defined its goals, it needs to measure progress towards those goals. KPIs provide a measurement tool.
| Architecture Diagram | Architecture diagram is a graphical representation of the concepts, their principles, elements and components that are part of an architecture.
| Architecture Draft | The high level draft of the system and solution architecture.
| Architecture Review Board Sign Off | The Architecture Review Board is a cross-organizational body to oversee the implementation of a coherent strategy and ensure compliance in systems. This body should be representative of all the key stakeholders in the architecture, and will typically comprise a group of executives responsible for the review and maintenance of the overall architecture.
| Align Business and Performance KPIs | Business and Performance KPIs alignment helps the organization to pull everyone and every process within the organization together in order to spend the least amount of time and effort to achieve business goals and fullfil its purpose.
| Alignment of the customer roadmap with project timeline | The customer roadmap is comprised of high level milestones and business goals. The project timeline must adhere and align with this over all strategy.
| AEM technical trainings | Technical trainings for developers, architects, engineers and business practicioners. | https://learning.adobe.com/catalog.html?solution=Adobe%20Experience%20Manager
| AEM Admin trainings | Trainings for administrative staff for the solution.
| AEM Author trainings | Trainings for the producers of content (authors) for the solution.
| AEM Certification Exam | Cerification exams for developers, architects, engineers and business practicioners.
| AEM Certified | Passing the certification exam.
| Application Architecture Definition | Application architecture describes the behavior of applications used in a business, focused on how they interact with each other and with users. It is focused on the data consumed and produced by applications rather than their internal structure.
| Application specific maintenance tasks defined | Apart from AEM standard maintenance tasks, this defines any other tasks that need to be executed for the operational maintenance of the solution.
| Appropriately trained staff | For project teams the recommendation is to have at least one AEM Lead Developer Certified and one AEM Architect Certified and the development team comprised of 75% certified developers. This allows for mentorship among the certified developers to junior developers and ensures knowledge share an transparency.
| Automation Strategy | The Automation Strategy outlines the deployment automation set up including cadence, tooling and environments. This ensures faster and consisent deployments.
| Automated Testing Strategy | The automated test strategy defines a framework for reusable automated scripts and the approach planned by the QA. It outlines the overall plan for automation testing to help ensure a higher ROI, more test coverage, and increased test reliability with quality repetition.
| Automated test suite adapted to real content and results compared to KPIs | Automation scripts and basic automated use cases adapted to production content and checked against the KPIs.
| Automated Testing Strategy validated against realistic and expected load | The strategy must be validated and adjusted according the actual load and content that will be on the solution.
| Aware of communication plan | The entire project team and stakeholders must be aware of the reporting structure, cadence of reporting and channels of communication.
| Aware of success definitions and criteria | The entire project team and stakeholders must be aware of the success definitions and criteria.
B
| Back up and Restore Concept | The Back up and Restore Concept outlines the technical functionality that will be implemented in the solution and is required by the Company back up and restore policy.
| Back up and Restore tested | A full end to end test of the Back up and Restore Concept.
| Business Case(s) | A business case is an argument, usually documented, that is intended to convince a decision maker to approve some kind of action. A business case document should examine benefits and risks involved with both taking the action and, conversely, not taking the action. The conclusion should be a compelling argument for implementation.
| Business KPIs | Business KPIs are measurable values that demonstrates how effectively a company is achieving key business objectives. Organizations use KPIs to evaluate their success at reaching targets.
| Business Requirements Documentation | A business requirements documentation (BRD) details the business solution for a project including the documentation of customer needs and expectations. The BRD distinguishes between the business solution and the technical solution. When examining the business solution the BRD should answer the question, “What does the business want to do?”
| Business sign off on any required adjustments to the solution or architecture identified and aligned against ROI and KPI expectations | The processes of the Risk Assessment and Penetration Test may produce issues and outcomes that need to be addressed in the architecture or development of the solution. Any adjustments coming out of these processes need to be reviewed and approved by the business and gauged against the over all goals.
C
| Caching Strategy | The Caching Startegy outlines what will be cached for the end user and is compliant with the Performance KPIs. Things such as images, javascript and other server files can be cached to improve the performance of a solution.
| Coding Guidelines | The Coding Guidelines outline basic pricipals that the developers adhere to in the development of the solution. This can include but is not limited to; naming conventions, service usage, and library usage.
| Communicate Operations Manual | Ensure that all required roles have received the Operationa Manual.
| Communicate Preformance Test Report | Ensure that all required roles have received the Performance Test Report.
| Communicate Release Notes | Ensure that all required roles have received the Release Notes.
| Communicate scope and expectations to team | Enusre that the project team is fully aware of and aligned with the project scope and expectations for delivery.
| Communicate training materials and user guides | Ensure that all required roles receive training materials and user guides.
| Customer Backup and restore policy | Policies from the business around data and solution back up, storage and restoration in case of failure.
| Customer Coding Guidelines | Any requirements from the business on how development should be done.
| Customer Monitoring Policies or Requirements | Policies and requirements from the business around what needs to be monitored in addition to any reccommendations in the Monitoring Concept.
| Customer Deployment/Release policies | Policies from the business around how and when deployments/releases can be made. This often includes timelines, scheduling and sign-off requirements.
| Customer Production Release Schedule | The schedule that is defined by the customer business or IT for releases to productive environments.
| Customer Reporting Policies or Requirements | Policies or requirements for reporting. This can include cadence and format.
| Customer Security Policies | Policies provided by the business and IT for security of the solution. This can include requirements for passing a riak assessment and penetration test as well security requirements such as escaping of all input fields, encryption usage (SSL), certificates, and authentication and sessioning.
| Customer Specification Guidelines | Any guidelines on the format, sign-off and delivery of specifications.
| Compliance to Security Concept | Ensure that Security Concept is in place.
| Compliance to Customer Security Requirements | Ensure that all Customer security based requirements are in place.
| Components and templates realtionship concept | The outline of the templates and components that will be used including inheritance rules, permissions and relationships.
| Components and Templates relationship Specification | Details of the Components and templates relationship concept.
| Components Specification | Details of each of the components to be implemented.
| Content Architecture Document | Documentation of the future architecture of the content including content tree, tagging concepts and content reuse strategy.
| Content validated for migration | The legacy system content is reviewed and the seleected content is validated for migration to the new solution.
| Contract Draft | Initial draft of the contract.
| Current Content Structure and Format | Documentation of the current content architecture and the format. This will be used to generate the future Content Architecture and will go into the Migration Concept.
| Customer Roadmap | Roadmap of major technological and major business milestones to be implemented.
| Customer Test Reports | Reports from the customer to the Quality Lead during the UAT period.
| Customizations that affect upgrades documented and hotfixes documented | AEM can be heavily customized to suit business need. Any customizations that may impact upgrading must be fully documented. An example would be major changes to the UI of AEM. All required cumulative fix pack (CFP), Service Packs, Upgrades, Hotfixes required for the solution must be fully documented.
D
| Daily UAT Report | Reports or meetings that outline the issues reported in UAT and prioritization of the issues.
| Default security enabled | AEM default security settings enabled.
| Deployment cadence establiished | The frequency of deployments established across environments.
| Deployment / Release Policies and Processes | Formalized and combined project deployment/release policies. These can include time for releases, holiday planning, and frequency and can depend on environment.
| Development Role Definition | Which developer and role is executing IT (performance or other) and/or Unit Tests with in the solution.
| Development Methodology | Software development methodology is a splitting of software development work into distinct phases (or stages) containing activities with the intent of better planning and management. It is often considered a subset of the systems development life cycle. The methodology may include the pre-definition of specific deliverables and artifacts that are created and completed by a project team to develop or maintain an application.
| Devolpment environment ready | Development environment is set with integrated tooling for automation of deployments.
| Dialogs Specification | Details for the dialogs of the solution.
| Document development environment set up | Documentation of the development environment.
| Document Production environment set up | Documentation of the production environment.
| Document test environment set up | Documentation of the test environment.
| Durabilty Test | The Durability Test shows the performance of the solution under the desired load. It then tests under the defined hreashold of load, gauging how long the solution survives under threshold load and at what performance levels.
| Durabilty Test Executed | Execution of the Durability Test.
E
| Error Handling Concept | Error handling refers to the anticipation, detection, and resolution of programming, application, and communications errors.
| Error Handling Documentation | Documentation of the Error Handling Concept.
| Escalation Processes | Defined processes of excalation for each of the project levels: project team, customer and Adobe.
| Exisitng Permissions structure | Documentation of the existing set of permissions and groups defined for the legacy solution or organizationally.
| Expected success definitions and cirteria | The Project Sponsor collects the business expectations for the success of the project. These can be anything from specifica KPIs such as percentage more pages served, lower time to publish for content or more high level goals such as easy to use interface. It is important to have the full set of expectations available at the start of a project as these should influence all decisions made throughout the implementation.
| Experience Designs Requirements | Requirements for the entire experience of the solution. This can mean personalization, cross device persistence and user experience.
| Experience Specifications | Details of the Experience Design Requirements.
| External System & User dependencies / System Context | A diagram or outline of the full ecosystem of the solution including the external integrations, interfaces, dependencies and networks.
| Existing Systems Map | A diagram of the exisitng systems and dependencies.
F
| Fallback system and procedure tested | End to end test of the fallback system
| Fallback system and procedure | The definition of the business critical functionalities that must keep operating in case of a critical failure and processes to roll over to them.
| Fallback system sign off from business stakeholders | Sign off that the fallback system and procedures will ensure the critical business functionalities.
| Feasability confirmation on KPI's | A study of AEM and the high level solution design against the KPIs to ensure that the KPIs can be met.
| Finalized Contract | Finalized and signed contract.
| Functionality of the solution are accepted by stakeholders | Full acceptance of the functionality and known issues in the solution.
G
| Go live Schedule | Timeline and schedule for the activites in preparation for go live and the actual go live.
H
| Happy Paths defined | A happy path is a default scenario featuring no exceptional or error conditions, and comprises the sequence of activities executed if everything goes as expected.
| Hardware Estimates | Estimations of the needed hardware for basic AEM installation and any additional requirements based on the high level solution design. | https://experienceleague.adobe.com/docs/experience-manager-65/deploying/introduction/technical-requirements.html?lang=en#introduction
| Hardware will be available to fullfil requirements | All environments will have the minimum required hardware in place for development.
| High Level Requirements | The high level requirements are the most generalized breakdown of requirements of the system. This level corresponds to major system functions or business processes. These functions are usually known and so this is generally not an estimate, but a known quantity.
| High Level Solution Design | High-level solution design explains the architecture that would be used for developing the solution. The architecture diagram provides an overview of an entire system, identifying the main components that would be developed for the product and their interfaces.
| High Level System Map | A very high level diagram of the system. This differs from the Solution Context in that there are no interfaces on this diagram but will have the general map of all systems involved.
| Historical Content Structure | The legacy system content structure for reference and use in the migration strategy.
| Historical performance and historical performance KPIs | The legacy system performance and KPIs. This are used for benchmarking the new solution and as reference.
I
| Identify critical key solutions/functionalities | A known list of the business critical functionalities.
| Inform Adobe Support about the Go live Schedule | Communicate with Adobe Support to ensure any support that is needed can be enabled during the go live.
| Implementation Concept | The Implementation Concept is the over all set of guiding principles for the implemenation and should take into consideration operations, maintenance, compatability, reusability, security and scalability. This can also outine the frameworks, libraries and other artifacts that are used in the solution.
| Implementation - Any needed changes based on Penetration Test Results | Implementation of required and signed off changes to the solution based on the results of the penetration test.
| Implementation - Automation Strategy | Set up of the tooling set and processes to support automation.
| implementation - Automated Testing Strategy | Set up of the tooling and processes to support automated testing.
| Implementation - Content Architecture | Implementation of the content architecture, tagging concepts and reuse.
| Implementation - Experience Design | Implementation of the requirements to support the Experience Design.
| Implementation - Fallback system and procedure | Implementation fo the fallback system and procedure.
| Implementation - Integration | Implementation of integrations with any external systems.
| Implementation - Migration Strategy | Migration and validation of content and other artefacts to the new solution.
| Implementation - Roles and Rights | Implementation of roles and rights, users and groups.
| Implementation - Security Concept | Implemantation of all security measures including default.
| Implementation - Security Software | Implementation of software application security.
| Implementation - System Architecture Security Concept | Implementation of the system security.
| Implementation - URL Handling | Implementation of the URL handling concept.
| Implementation - Workflows | Implementation of the designed workflows.
| Initial Experience Designs | Preliminary concepts for the Experience Designs.
| Integration Testing | Testing and confirmation of all integrations internal and external. This should be automated and run frequently to ensure system stability.
| Issue tracking system and processes | A shared system of record that all project stakeholders have access to in order to facilitate transparency of the project status and that any issues are addressed. Examples are JIRA and HP Quality Center.
| Issue tracking system process is set up and integrated | What ever tooling is selected is fully integrated and access granted to all required roles.
J
K
L
| Legacy System | Legacy system is an old method, technology, computer system, or application program, "of, relating to, or being a previous or outdated computer system."
| List of standard development tools to be used in the project | An outline of what will be used in the implementation. This should include documentation tools, issue tracking, deployment and build tools.
| List of users that require access to Adobe Support Portal | All required users and roles that will need access to the Support Portal. This is normally the Solution Architect or customer IT staff.
| Log File Analysis | An analysis and recommendation for the level of granualarity required for the monitoring of the solution.
M
| Maintenance tasks specific to AEM tested and enabled | Tasks such as compaction, system clean and workflow purging are tested and enabled.
| Migration Strategy | A full outline of the existing content, content architecture and formats mapped to the new solution. It contains technical details of automated migration if possible and migration smoke tests to perform after to validate the migrated content. It will also recommend a a manner of maintaining the content as up to date as possible during migration but before go live of the new system. This can mean a content freeze, double poublishing, or the maintenance of an alpha.
| Migration Plan | Timeline for the migration. Content maintenance plan out lined in the strategy implemented.
| Mocking Concept of external Interfaces | A concept to test and develop against any external interfaces that may not be open to the development or test environments to ensure as close to production like behavior as possible.
| Monitoring - CPU | Monitoring of the usage of the system CPU by the solution.
| Monitoring - Disk I/O | Monitoring of the usage of the system Disk I/O by the solution.
| Monitoring - Disk space | Monitoring of the usage of the system Disk Space by the solution repository.
| Monitoring - External system | Monitoring of the external systems connections.
| Monitoring - Network Bandwith | Monitoring of the usage of the system network bandwidth.
| Monitoring - Requests | Monitoring of requests to the solution.
| Monitoring - Security Points | Monitoring at the defined security points.
| Monitoring - System | Monitoring of the overall system and alerts.
| Monitoring - Threshold and interventation | Monitoring of the solutions defined threshold and implementation of intervention steps to reduce load.
| Monitoring Concept | The over concept of monitoring incorporating AEM basic monitoring, system monitoring and customer requirements.
| Monitoring Policy communicated to System Engineer | The system engineers and operations staff must know and understand any customer monitoring policies.
| Monitoring Points in the application defined | Specific points that could be succeptable to failure defined and monitoring defined. Examples include, key workflows, transactions processing and integration points.
| Monitoring Reports structure in place | Structure of who and when monitoring reports should be generated and delivered to.
N
O
| Operations Manual | Overall operational tasks, key contacts, deployment plans, pre-post deployment checklists and any other critical tasks for the operations and maintenance of the solution.
| Operational tasks documentation | All operational tasks documented and frequency defined.
P
| Package Prepared | Software package built and delivered for deployment.
| Performance Benchmark | The Performance Benchmark assesses the performance characteristics of the solution and system hardware. This is used to define performance testing, durability testing and monitoring.
| Performance KPIs | KPIs required around the performance of the system. Some examples are page load time, server response time, and database query performance.
| Performance and scalability concept | Conceptual document for implementation to meet the perfornance KPIS as well as how to scale the solution to continue to meet those KPIs.
| Performance Test Report | Reports created for the business explaining the performance test results.
| Performance Test Results match Performance KPIs | The results must match the defined KPIs and expectations for performance.
| Penetration Test | A penetration test, informally pen test, is an attack on a computer system that looks for security weaknesses, potentially gaining access to the computer's features and data.
| Penetration Test Results | Reports created for the business explaining the penetration test results.
| Penetration Test passed | All required criteria are passed.
| Persona based Testing Concept | A method of testing based on the different personas outlined in the Experience Designs as well as for authors and permissions levels. This is often used in UAT.
| Post-Deployment Checklist | Series of checks and tasks to perform after each deployment.
| Pre-Deployment Checklist | Series of checks and tasks to perform before each deployment.
| Production environment ready | Test environment is ready with automated deployments in place.
| Production environment baseline performance tests | A baseline test is usually run on a plain installation of AEM. This is used to benchmark against the implementation and hardware.
| Production Sign off Process and Policy | Policy and process of how to obtain the Production Sign off to move the package to the production environment.
| Production Sign off from business stakeholders | Before going to the production environment, Production Sign off (PSO) is granted. This is a review of the current release and known issues that will go into production. Sign off is given as part of the go live schedule.
| Project communication plan | Communication plan for both businesss stakeholders and project team.
| Project efforts initial estimates | High level estimations of the high level requirements for the implementation.
| Project efforts final estimates | Final estimates from each project lead for the detailed implementation. This will include project manangement, consulting, architecture, and testing efforts as well as development.
| Project Ogranization | A chart outlining the organization and reporting structure of the project and team.
| Project Scope Document | Project scope is the part of project planning that involves determining and documenting a list of specific project goals, deliverables, features, functions, tasks, deadlines, and efforts. It is what needs to be achieved and the work that must be done to deliver a project
| Proof of Concept (POC) | The POC is a realization of a certain functions of the solution to demonstrate its feasibility and verify that there is the potential of being used.
| POC tested and verified against Requirement Documentation | The POC is used to gauge against the requirements to ensure that both are aligned.
| Project status reports within a defined cadence | Status reports delivered in the agreed time and format.
| Purge Rules | AEM maintains versions of assets and content. Purge Rules are designed and configured to periodically purge the system of older versions in order to maintain repository health and size.
Q
R
| Release running on production environment | Final release running in production and active.
| Release Notes | The documentation for the release that includes all prerequisites for, requirements included, issues solved and known issues in the release. It is used with the Runbook to execute pre and post installation steps and checks.
| Release Coordinated | The project manager coordinates all roles required for the release to production.
| Relevant contract terms | Contract terms that are relevant to the implementation of the project such as contractual milestones, invoice periods or staff requirements.
| Reporting Cadence | The frequency of reports delivered to the customer.
| Respository Optimization | Data is never overwritten in a tar file, the disk usage increases even when only updating existing data. To make up for the growing size of the repository, an optimization strategy is put in place to manage the growth of the repository by removing obsolete data.
| Requirements Documentation | Functional and non-functional requirements documented and efforts estimated.
| Resources available to support go live | All required roles for go live are staffed and available.
| Risk Assessment | The Risk Assesment is executed by the customer IT or Security department. It covers the technical and business risks of the project. The assesment is normally a hurdle to overcome for the solution to ensure compliance to security policies.
| Risk Mitigation Plan | The Risk Mitigation Plan includes the Risk Assessment, any identified risks and possible solutions to those risks should they arise in the implementation.
| ROI expectations | Expectations of the return of investment on the solution.
| Roles and Rights Concept | High level outline of users, roles, permissions and groups as well as user management and provisioning.
| Roles and Rights Specification | Detailed specification of the Roles and Rights Concept
| Roles and Rights Concept meets security guidelines | Review of the Roles and Rights concept to ensure that it meets the security policies.
S
| Security Architecture Recommendations | Recommendations around security for software and hardware architecture.
| Security Based Coding Guidelines | Any guidelines of how the development coding should be done based on security requirements such as naming conventions, libraries or guidelines for frameworks or API usage.
| Security Checklist | Checklist of items based off of the concept and any policies to ensure compliance of the solution. This is often included as part of the post deployment steps in the runbook as well.
| Security Concept | Details of the security set up of the application, architecture and infrastructure.
| Security Concept Draft | The high level outline of the security set up of the application, architecture and infrastructure.
| Security issues listed and assesed | All security issues of the solution listed and assesed including effort estimates.
| Security sign off from business stakeholders | Sign off from the stakeholders to ensure that the security implementation is compliant with policies and expectations.
| Setup Support processes | Support processes and communication paths set up to all partners, the customer and Adobe.
| SLAs for third party systems | Service Level Agreements are available and communicated to the development and operations team for implementation and support.
| Smoke Test Concept | A set of defined steps to execute after installation or deployment to any environment that test the key functionalities of the solution to ensure basic operations and functionality of the solution.
| Smoke Tests executed for system validation | Smoke Tests run on all systems to ensure basic functionality of the solution on installation or deployment to any environment.
| Solution Review Board established and meeting cadence set | The Solution Review Board is usually comprised of customer stake holders. The meetings are used to review the current scopedd requirements and relevant specifications to ensure alignment with the success definition and criteria and provide input into the development of the requirements.
| Solution Runbook | The installation instructions for the solution and basic operational tasks to be executed on installation.
| Solution sign off and accpetance process | The sign off and acceptance process outlines the gateway criteria for the release of the solution into a productive environment. It can also serve as a contractual milestone.
| Software Architecture Startegy | The high level strategy of the software architecture including services, servlets, frameworks and other implementation decisions.
| Special functionality concept | The initial concept for any special functionality that is considered outside the normal scope of development on the AEM platform.
| Special Functionality Specification | Details of any special functionality that is considered outside the normal scope of development on the AEM platform.
| Specification Guidelines | Any guidelines from the customer on how specification should be done apart from the project guidelines.
| Specification review and approval process defined and communicated | A clear process for sign off of specifications with the customer will be put in place. This ensures clarity and firmness of scope for requirements.
| Staff selected for AEM Admin Training | Internal staff that will need the first round of training to administer the solution.
| Staff selected for author & end user training | Internal staff that will need the first round of training on the solution.
| Stakeholders | Key persons and roles internal and external that have interest in the project.
| Stakeholders are aware of succes definitions and criteria | All stakeholders outside of the implementation team are in alignment with the success definition and criteria.
| Stakeholders understand project and expectations | All stakeholders outside of the implementation team are in alignment with the overall project and expectations, both internal to the project team and to the customer.
| Status Report format definition | Status reports are key tools of communication. The format should be aligned with any reporting requirements of the customer.
| Success criteria and definition | The customer, project sponsor and project manager or consultant should outline what the a successful outcome of the project is and what the specific criteria are to meet that definition of success are. These are used for the basis of KPIs and decisions made throughout the implementation to ensure that the criteria for success are met.
| Support processes and access to Adobe Support Portal | Access to the Adobe support portal for key members of the team is crucial to submit tickets and issues to Adobe to address any product based issues that may come up during implementation.
| Support in validation of reported issues | Part of the Quality Leads responsibilities are to ensure that there are resources available to support any user or UAT reported issues and validate them against the test environment.
| System Architecture Definition | An initial proposal and definition of how the system for the solution will be architected for all environments,
| System Architecture Documentation | A document of the system architecture including interfaces, network location and integrations for all environments.
| System Architecture Security Concept | A high level outline of how the system architecture will be compliant with any security policies. This can include firewalls and firewall rules, secutiy zones, local and general traffic managers, web servers, proxies and reverse proxies.
| System risk factors identified and verified | Any risk factors found in the risk assesment or other reviews are identified and assessed to the level of risk implied in each one and effort estimated for any changes to the implementation to address them.
T
| Team is aware of the commmunication plan | All members of the team are aware of how and who should be communicating with the customer and when.
| Team is aware of succes definitions and criteria | Alignment with the customer defined success definition and criteria. All roles on the team must be clear on these expectations.
| Team understands project and expectations | Alignment with the overall project and expectations, both internal to the project team and to the customer.
| Technical risk factors verified | Technical risks can include cross site scripting, end user facing input fields, infrastructure, technology age, number of integrations, and dependencies.
| Technical Requirements | Requirements specific to technical implementation of services that support the solution.
| Technical Specification | The Technical Specification covers interfaces, configurations, APIs and services that support the requirements of the solution.
| Template Specification | The detailed specifications for templates including parsys, blueprint and inheritance mapping. The specification is based off of the Business Requirements and Experience Requirements.
| Test Cases | The Test Cases are the detailed steps to execute functional testing of the solution.
| Testing Concept | The Testing Concept is the very high level outline of all testing for the project including QA, UAT, performance, security, and integration testing.
| Test Content | The Test Content should be as close to production content as possible.
| Testing Plans | The Testing Plans outline in greater detail execution of tests for each phase of development and are based on the Testing Strategy.
| Test environment ready | Test environment is ready with automated deployments in place to ensure all release candidate code is up to date for testing.
| Testing Scope | The defined scope for what will be covered and by what role in the Testing Strategy.
| Testing Strategy | The Testing Strategy outlines the high level strategy for quality assurance and user acceptance testing including timelines, reporting cadence, and execution.
| Test Suite | Automation suite and tooling selected for use case automation and other test execution tasks.
| Test Reports | Reports covering defects raised, status of test cases gone through, and other quality related topics
| Third party systems access enabled | Access levels granted to respective roles for third party systems.
| Third party integration concept | Architectural and system level concept for third party systems,
| Third party integration Specification | Details of the funcional and non-funcational requirements for the functionality supported and integration of the third party systems.
| Third party security concept | Concept for ensuring security of any third party integrations that is compliant to any security policies.
| Third party system for integration | All third party systems are available with documentation for integration implementation.
| Thirday party Testing Concept | Defines use cases for testing the integrations and functionality related to any third party application.
| Threshold definition | Defines the key values for monitoring points in the system. For example, how many kilobytes (KB) of unsent logs generate a warning on the principal server instance or the number of milliseconds of average delay per transaction that are tolerated before a warning is generated on the principal server.
| Timeline and Milestones | A guide of the project cadence and contractual milestones that are used as points for invoicing and alignment against the success definitions and criteria as well as KPIs.
| Total project efforts | All effort estimates consolodated from each of the leads on a project including, overhead, development, system engineering, architectural and testing efforts. If there is a support level included in the agreement, support and operations efforts should be included.
| Training Materials | Materials created specific to the solution to be used in training sessions in conjuction with the User Guides.
U
| Understands scope of project and expectations | Each role in the project should confirm that they understand fully the scope of the project and the expectation from the customer and this is the basis for all decisions made per role, per phase in the project.
| URL handling concept | The URL handling concept will cover AEM specific URL functionalities including; vanity URLS, link externalizing, error pages and mapping. The concept will also include any rewrite rules or virtual hosts on the web server. It should also include SEO consideration such as robots.txt and a site map.
| Use cases | A use case is a list of actions or event steps, typically defining the interactions between a role and the solution, to achieve a goal. The role can be a user or an external system.
| Use Cases converted into test scenarios | Test scenarios that are based on the technical and business use cases are used to test the soltuion behavior as it is expected in the most common uses.
| User Guides | User Guides are materials produced for the end users of the solution. They are created for administrators, power users, authors and end users.
V
| Validated budget plan | All stakeholders have reviewed and validated the budget plan for invoicing, amounts and budget reporting.
W
| White box test results | White-box testing is a method of testing software that tests internal structures or workings of an application, as opposed to its functionality. White-box testing can be applied at the unit, integration and system levels of the software testing process.
| Workflows concept | Workflows enable automation of Experience Manager activities. The Workflows Concept outlines the processes that will need automation as well as the services and roles in AEM that will be affected. | https://experienceleague.adobe.com/docs/experience-manager-65/administering/operations/workflows-administering.html?lang=en#operations
| Workflow Specification | Based on the Workflows Concept the Workflows Specification goes into deep detail of the steps that will create the full workflow. The specification of workflows should include use case, roles, steps, outcomes and error handling for workflows.
X
Y
Z

## Persona Definitions
Project Personas
Persona | Definition
Project Sponsor | The project sponsor is responsible for the business case of the project. They will help to shape and define the scope, the success definition and criteria as well as the main KPIs. They will provide the main milestones based on the client roadmap.
Project Manager | The project manager is responsible for the overal delivery of the project based on the scope, success definition and criteris and KPIs provided by the project sponsor. They are responsible for defining the budget and resourcing the project based on the budget. They are the main point of communication for all roles in the project.
Architect | The solution architect is responsible for the over design of the solution and system. They help to define the implementation strategy for AEM. For example, to go with a cluster installation or a cold standy or if a CDN is needed. They also define the AEM solution architecture based on the client requirements such as the roles and rights concept and the template and components relationship or to use multi site management.
Business Analyst | The business analyst is primarily responsible for gathering and analyzing high level requirements and transforming those into specifications for the development team to work from and for the project manager to plan development with. The busniess analyst works closely with the client to analyse the requirements and match them against the success definition and criteria and keeps in mind the KPIs both business and performance based.
Development Lead | The development lead is responsible for the technical delivery of the project. They are responsbile for selecting the development methodology inline with the client requirements. They craft the development strategy aligned with the business and performance KPIs and take into account the success definition and criteria. The development lead works closely with the architect in especially on the development strategy in AEM such as temaplates and components relationships and integration strategy for 3rd party applications and special functionality.
Quality Lead | The quality lead is responsible for the quality of the delivery and ensuring that it meets the criteris for success and KPIs set by the client. The quality lead sets the quality metrics, aligns with all stakeholders and defines and exectutes the testing plans. The quality lead creates and delivers reports to project stakeholders.
System Engineer | The systems engineer is responsible for the oversight of the infrastructure of the project. The set up the internal development and test environements, are responsible for matching those systems to the client systems. The provide hardware recommendations, monitoring implementation and providing operations support for go live and after.
Security Lead | The security lead is responsible for the over all security concept of the solution and ensuring that it is aligned with any requirements and policies from the client. They devilver a security concept, security operations and recommendations for any hardware based security concepts such as zones and firewalls.